## Budget Summary
PROJECT BUDGET SUMMARY
Bottoms-up build cost (pre-tax) — cross-references Resource Plan & Other Costs
Cost Block | Amount (₹) | % of Pre-Tax Budget
A. Personnel (delivery team) | 28280000 | 69.86%
B. Non-Personnel (infra, tools, integrations, marketing) | 9200000 | 22.73%
Sub-Total (A + B) | 37480000 | 92.59%
Contingency / Management Reserve @ 8% | 2998400 | 7.407%
TOTAL PROJECT BUDGET (Pre-Tax) | 40478400 | 100%
GST (18%) is shown in the client-facing Quotation sheet; it is recoverable as input tax credit and excluded from the internal build budget.

## Phase Quotation
PHASE-WISE QUOTATION
Pre-tax budget allocated across delivery phases, plus GST to arrive at the all-inclusive quotation
# | Project Phase | Key Deliverables | Duration | % of Budget | Phase Cost (₹)
1 | Initiation & Discovery | Project charter, kickoff, governance setup, vision workshop | Month 1 | 4% | 1619136
2 | Requirements & Analysis | BRD, SRS, FRD, process maps, backlog, RTM | Months 1–2.5 | 7% | 2833488
3 | UX / UI Design | Wireframes, prototypes, design system, usability testing | Months 2–3.5 | 9% | 3643056
4 | Architecture & Environment Setup | Solution architecture, CI/CD, cloud landing zone | Months 2–3 | 6% | 2428704
5 | Core Platform Development | Catalog, search, cart, checkout, orders, accounts, admin | Months 3–8 | 34% | 13762656
6 | Supply Chain & Integrations | Inventory/WMS, payments, logistics, ERP, notifications | Months 5–8 | 10% | 4047840
7 | Testing & QA | Functional, regression, performance, security, automation | Months 6–9 | 9% | 3643056
8 | UAT, Security Audit & Deployment | UAT, VAPT, performance sign-off, prod cut-over | Months 9–10 | 7% | 2833488
9 | Marketing & Go-Live | Campaigns, ASO/SEO, launch, app-store release | Months 9–11 | 11% | 4452624
10 | Hypercare & Stabilization | Production support, defect triage, handover | Month 11 | 3% | 1214352
| Sub-Total (Pre-Tax) |  |  | 100% | 40478400
| GST @ 18% |  |  |  | 7286112
| GRAND TOTAL QUOTATION (Incl. GST) |  |  |  | 47764512

## Payment Schedule
MILESTONE-LINKED PAYMENT / DISBURSEMENT SCHEDULE
Disbursements released against milestone acceptance — % of all-inclusive quotation
Milestone | Acceptance Trigger | Target | % of Total | Amount (₹)
M0 – Mobilization | Charter signed, team & governance mobilized | Month 1 | 10% | 4776451.2
M1 – Requirements & Design Sign-off | SRS, FRD & UX prototype approved | Month 3.5 | 15% | 7164676.8
M2 – Architecture Baseline | Architecture + CI/CD + Sprint 1–2 demo | Month 4 | 10% | 4776451.2
M3 – MVP Feature-Complete (50%) | Core commerce flows demoable in staging | Month 6 | 20% | 9552902.4
M4 – Build Complete (100%) | All features + integrations code-complete | Month 8 | 20% | 9552902.4
M5 – QA & UAT Sign-off | Test exit + UAT acceptance + VAPT closed | Month 10 | 12% | 5731741.44
M6 – Go-Live | Production launch, web + apps live | Month 11 | 8% | 3821160.96
M7 – Final Acceptance | Hypercare complete, handover signed | Month 11 | 5% | 2388225.6
TOTAL |  |  | 100% | 47764512

## Resource Plan
PROJECT HORIZON — RESOURCE & PERSONNEL PLAN
Meridian Retail Pvt. Ltd. ¦ ShopSphere E-Commerce Platform ¦ Blended India CTC rates (FY 2025-26), all figures in INR
# | Role / Discipline | Head- count | Monthly Cost-to-Co. (₹) | Person- Months | Total Cost (₹) | Engagement Window
1 | Project Manager (IT) | 1 | 250000 | 11 | 2750000 | M1–M11 (full project)
2 | Business Analyst | 1 | 160000 | 8 | 1280000 | M1–M8 (front-loaded)
3 | Solution / Technical Architect | 1 | 280000 | 9 | 2520000 | M1–M9
4 | Scrum Master | 1 | 140000 | 9 | 1260000 | M2–M10
5 | UX / UI Designer | 2 | 120000 | 12 | 1440000 | M1–M7
6 | Frontend Developer (Web) | 4 | 130000 | 28 | 3640000 | M3–M9
7 | Backend Developer (Microservices) | 5 | 150000 | 38 | 5700000 | M3–M10
8 | Mobile Developer (iOS + Android) | 3 | 140000 | 21 | 2940000 | M3–M9
9 | DevOps / SRE Engineer | 2 | 160000 | 16 | 2560000 | M2–M11
10 | Data / Supply-Chain Engineer | 1 | 170000 | 7 | 1190000 | M4–M10
11 | QA / Test Engineer | 4 | 100000 | 24 | 2400000 | M5–M10
12 | Security & Compliance Specialist | 1 | 200000 | 3 | 600000 | M8–M10
| TOTAL PERSONNEL COST | 26 |  | 186 | 28280000
Blue figures are editable assumptions (monthly CTC, person-months). All totals are live formulas.

## Other Costs
NON-PERSONNEL COSTS
Infrastructure, tooling, integrations, security, data, marketing & launch — all figures in INR
# | Cost Category | Description / Basis | Amount (₹)
1 | Cloud Infrastructure | Dev/Staging/Prod on cloud; compute, DB, CDN, storage (11-mo ramp) | 1800000
2 | Software Licenses & Tools | Jira, Confluence, Figma, GitHub Enterprise, CI/CD, APM/monitoring | 650000
3 | Third-Party Integrations & APIs | Payment gateway, SMS/WhatsApp/email, logistics & shipping, maps | 900000
4 | Security Audit & Compliance | VAPT, PCI-DSS readiness, DPDP Act review, source-code review | 750000
5 | Testing Tools & Device Lab | Cross-browser cloud, load/performance tools, mobile device lab | 450000
6 | Data Migration & Integration | Legacy catalog, customer & order migration; ERP/WMS connectors | 500000
7 | Marketing & Launch | Digital ads, ASO/SEO, influencer, creatives, launch event | 3500000
8 | Training & Documentation | CS/ops enablement, admin & user manuals, runbooks | 300000
9 | Hardware & Contingency Misc. | Workstations, secure access, miscellaneous provisioning | 350000
| TOTAL NON-PERSONNEL COST |  | 9200000