## Milestones
PROJECT HORIZON — MILESTONE SCHEDULE
Meridian Retail Pvt. Ltd. ¦ ShopSphere E-Commerce Platform ¦ 11-month delivery (assumed start: Jul 2026)
# | Milestone | Target Month | Calendar (indicative) | Gate / Exit Criteria
M0 | Project Mobilization & Charter Sign-off | Month 1 | Jul 2026 | Charter approved, team onboarded, governance live
M1 | Requirements Baseline (SRS + FRD + RTM) | Month 2.5 | mid-Sep 2026 | SRS, FRD, backlog & RTM signed off by sponsor
M2 | UX Design & Prototype Approval | Month 3.5 | mid-Oct 2026 | Design system + clickable prototype approved
M3 | Architecture Baseline & CI/CD Ready | Month 4 | Oct 2026 | Architecture approved, environments + pipeline live
M4 | MVP Feature-Complete (Core Commerce) | Month 6 | Dec 2026 | Catalog–cart–checkout–orders demoable in staging
M5 | Build Complete & Integrations Done | Month 8 | Feb 2027 | All features + payments/logistics/ERP integrated
M6 | System & Performance Test Exit | Month 9 | Mar 2027 | Test exit met, P1/P2 defects = 0, NFRs verified
M7 | UAT Sign-off & Security Clearance | Month 10 | Apr 2027 | UAT accepted, VAPT closed, PCI-DSS readiness
M8 | Go-Live (Web + iOS + Android) | Month 11 | May 2027 | Production launch, app-store release, marketing live
M9 | Hypercare Exit & Final Acceptance | Month 11 | May 2027 | Stabilized ops, handover & sign-off complete

## Task Distribution
WORK BREAKDOWN & TASK DISTRIBUTION
Owner = accountable role ¦ Status drives the project dashboard ¦ Effort in person-weeks
WBS | Task / Work Package | Phase | Owner (Role) | Start | End | Effort (p-wks) | Dependency | Status
1.1 | Project charter & governance setup | Initiation | Project Manager | M1 | M1 | 3 | — | Done
1.2 | Kickoff & vision/scope workshop | Initiation | Project Manager | M1 | M1 | 2 | 1.1 | Done
2.1 | Stakeholder interviews & elicitation | Requirements | Business Analyst | M1 | M2 | 6 | 1.2 | Done
2.2 | BRD, SRS & FRD authoring | Requirements | Business Analyst | M2 | M2 | 8 | 2.1 | In Progress
2.3 | Product backlog & RTM | Requirements | Business Analyst | M2 | M3 | 4 | 2.2 | In Progress
3.1 | Information architecture & user flows | Design | UX/UI Designer | M2 | M3 | 5 | 2.2 | In Progress
3.2 | Wireframes & clickable prototype | Design | UX/UI Designer | M3 | M3 | 6 | 3.1 | Not Started
3.3 | Design system & usability testing | Design | UX/UI Designer | M3 | M4 | 5 | 3.2 | Not Started
4.1 | Solution architecture & tech selection | Architecture | Solution Architect | M2 | M3 | 5 | 2.2 | In Progress
4.2 | Cloud landing zone & CI/CD pipeline | Architecture | DevOps Engineer | M3 | M4 | 6 | 4.1 | Not Started
5.1 | Identity, accounts & authentication | Development | Backend Developer | M3 | M5 | 8 | 4.2 | Not Started
5.2 | Product catalog & search service | Development | Backend Developer | M4 | M6 | 12 | 5.1 | Not Started
5.3 | Cart, pricing & promotions engine | Development | Backend Developer | M4 | M6 | 10 | 5.1 | Not Started
5.4 | Checkout & order management | Development | Backend Developer | M5 | M7 | 12 | 5.3 | Not Started
5.5 | Web storefront UI build | Development | Frontend Developer | M3 | M8 | 24 | 3.3 | Not Started
5.6 | iOS & Android app build | Development | Mobile Developer | M3 | M9 | 24 | 3.3 | Not Started
5.7 | Admin & merchandising console | Development | Frontend Developer | M5 | M8 | 10 | 5.2 | Not Started
6.1 | Inventory & supply-chain module (WMS) | Integration | Data/SC Engineer | M5 | M8 | 10 | 5.2 | Not Started
6.2 | Payment gateway integration | Integration | Backend Developer | M6 | M7 | 6 | 5.4 | Not Started
6.3 | Logistics, shipping & tracking APIs | Integration | Backend Developer | M6 | M8 | 6 | 5.4 | Not Started
6.4 | ERP/CRM & notification services | Integration | Backend Developer | M6 | M8 | 6 | 6.1 | Not Started
7.1 | Test planning & automation framework | Testing | QA Engineer | M5 | M6 | 5 | 2.3 | Not Started
7.2 | Functional & regression testing | Testing | QA Engineer | M6 | M9 | 16 | 5.4 | Not Started
7.3 | Performance & load testing | Testing | QA Engineer | M8 | M9 | 5 | 6.4 | Not Started
7.4 | Security testing (VAPT) | Testing | Security Specialist | M8 | M9 | 4 | 6.2 | Not Started
8.1 | Data migration & dress rehearsal | Deployment | DevOps Engineer | M9 | M10 | 5 | 7.2 | Not Started
8.2 | User acceptance testing (UAT) | Deployment | Business Analyst | M9 | M10 | 6 | 7.2 | Not Started
8.3 | Production cut-over & go-live | Deployment | DevOps Engineer | M10 | M11 | 4 | 8.2 | Not Started
9.1 | Pre-launch marketing & ASO/SEO | Marketing | Marketing Lead | M9 | M11 | 8 | 3.3 | Not Started
9.2 | Launch campaign & app-store release | Marketing | Marketing Lead | M11 | M11 | 4 | 8.3 | Not Started
10.1 | Hypercare & defect triage | Hypercare | Project Manager | M11 | M11 | 4 | 8.3 | Not Started
10.2 | Handover, runbooks & closure | Hypercare | Project Manager | M11 | M11 | 2 | 10.1 | Not Started
| TOTAL ESTIMATED EFFORT (person-weeks) |  |  |  |  | 241

## Gantt
HIGH-LEVEL GANTT — 11-MONTH ROADMAP
Each bar = active months for the work package ¦ Colour = phase ¦ ◆ = milestone gate
Phase / Work Package | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11
Initiation & Discovery | bar: M1
Requirements & Analysis
UX / UI Design | bar: M2 to M4
Architecture & Setup
Core Platform Development | bar: M3 to M8
Mobile Apps Development
Supply Chain & Integrations | bar: M5 to M8
Testing & QA
UAT, Security & Deployment | bar: M9 to M11
Marketing & Go-Live
Hypercare & Stabilization | bar: M11
◆ Milestone Gates | bar: M1; M3 to M4; M6; M8 to M11
Legend:
| Initiation |  | Requirements |  | Design |  | Architecture |  | Development |  | Integration
| Testing |  | Deployment |  | Marketing |  | Hypercare

## RACI
RACI RESPONSIBILITY MATRIX
R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed
Activity | Sponsor | PM | BA | Architect | Dev Lead | UX Lead | QA Lead | DevOps | Mktg Lead
Business case & funding | A | C | C | I | I | I | I | I | C
Charter & scope | A | R | C | C | I | I | I | I | I
Requirements (SRS/FRD) | C | A | R | C | C | C | C | I | C
UX design & prototype | I | A | C | C | I | R | C | I | C
Solution architecture | I | A | C | R | C | I | C | C | I
Development & code | I | A | C | C | R | C | I | C | I
Integrations | I | A | C | R | R | I | C | C | I
Testing & QA | I | A | C | C | C | I | R | C | I
Security & compliance | A | R | C | C | C | I | C | C | I
Deployment & go-live | A | R | I | C | C | I | C | R | C
Marketing & launch | A | C | I | I | I | C | I | I | R
Change control | A | R | C | C | C | C | C | C | C